## Active
Runninng Projects (Consultation, Cooperation, Traceability)
Project no. | Type | Title | Project Status | Dates | Coord. NMI (and Country) | Coordinator | Participants Countries | Participants NMIs | Action, comment | Status at the end of February 2002 | Comments for presentation to the EM TC meeting, 15-16 October 2002 | Comments and actions after the Euromet EM TC meeting, 15-16 Oct 2002 | Updates to the end of Febr. 2003 | Comments included in the Annual Report 2003 | EUROMET TCEM Meeting in Vienna, 25-26 November 2003 | EUROMET TCEM Meeting in Warsaw, 14-15 October 2004 | EUROMET TCEM Meeting in Bern, 13-14 October 2005 | EURAMET TCEM Meeting in Istanbul, 13-14 October 2011
1168 | Cooperation | Using Agilent 3458 multimeter for precision sampling in calibration laboratories |  | Dec 10 | MIRS (SI) | Rado Lapuh | SI, SE, FI, DE, IT, UK, NL, TR, RS | MIRS, SIQ, SP, MIKES, PTB, INRIM, NPL, VSL, UME, DMDM | Progress report not yet received Draft of the ‘sampling power cookbook’ is expected by the end of Dec 2012.
644 | Traceability | Traceability of Electrical Quantities |  | 2002-03-01 | BEV (AT) | W. Waldmann | AT, DE | BEV, PTB | New template was provided | The BEV National Standards of AC/DC transfer (voltage and current), Electrical Power and Energy, Inductance, Voltage and Current Transformers will be regularly calibrated at PTB. | No update available | Progress form to TC chairman before end of Feb. 2003 | National standards of BEV were calibrated at PTB for the following quantities: AC/DC-Transfer, Electrical Power and Energy, Voltage and Current Transformer ratios. | National standards of BEV are calibrated at PTB for the following quantities: AC/DC-Transfer, Electrical Power and Energy, Voltage and Current Transformer ratios. | Ongoing. Comment BEV: In 2003 no calibrations of national standards in the field of electricity were done at PTB. It was decided to write a short progress report every year. | ongoing | ongoing
682 | Traceability | Traceability of electrical quantities |  | 10 Sep 2002 | OMH (HU) | András Jakab | HU, AT | OMH, BEV | New template not yet received |  | The DC Voltage standard of Hungary (at 1.018V and 10V) will be calibrated at BEV on a regular time schedule. | No further action requested at this time | No update on this project | The DC Voltage standard of Hungary (at 1.018V and 10V) will be calibrated at BEV on a regular time schedule. | It was decided to write a short progress report every year. | ongoing | ongoing
701 | Traceability | Traceability of Electrical Quantities |  | March 2003 | OMH (HU) | A. Jakab | HU, DE | OMH, PTB | New template not yet received |  |  |  | The Technical Committee meeting will be held in Vienna on 25 and 26 November 2003 | The AC Power and Energy national standards of Hungary will be calibrated at PTB on a regular time schedule | Please note: Due to a change in the EUROMET Data Base the Project number changed (formerly 700). It was decided to write a short progress report every year. | ongoing | ongoing
752 | Traceability | Calibrations on high DC currents |  | Oct 2003 | PTB (DE) | H. Bachmair | DE, CH | PTB, METAS | New template was provided | [5 empty] | It was decided to write a short progress report every year. | ongoing | ongoing
755 | Traceability | Calibration of RF noise source reference standards |  | Dec 2003 | PTB (DE) | U. Stumper | DE, UK | PTB, NPL | New template was provided | [5 empty] | It was decided to write a short progress report every year. | ongoing | ongoing
757 | Traceability | Calibrations on high DC voltages and on instrument transformers |  | Oct 2003 | NPL (UK) | J. Williams | DE, UK | PTB, NPL | New template not yet received | [5 empty] | It was decided to write a short progress report every year. | ongoing | ongoing
796 | Traceability | Calibration of AC/DC transfer standards |  | June 2004 | SMU (SK) | P. Vrabcek | SK, DE | SMU, PTB | New template not yet received | [6 empty] | ongoing | ongoing
845 | Traceability | Traceability on electrical quantities |  | June 2005 | INM (RO) | Gelu Popovici | RO, TR | RO, TR | New template not yet received | [7 empty] | ongoing
1001 | Traceability | Agreement of traceability in measurement fields, including DC voltage, DC resistance, impedance between Metrosert and MIKES |  | July 2007 | Metrosert (EE) | Heikki Isotalo MIKES | FI, EE | MIKES, METROSERT | New template was provided
1077 | Traceability | Traceability on electrical quantities (high frequency noise, antenna calibrations) |  | Oct 2008 | Nmi-VSL (NL) | Gert Rietveld | NL, UK | NL, UK | New template not yet received | [7 empty] | ongoing
1194 | Traceability | calibrations on high ohmic resistors with values larger than 1 GOhm for PTB and customers of PTB. |  | May 2011 | PTB (DE) | Bernd Schumacher | CH, DE | PTB, METAS | New template was provided
1263 | Traceability | Traceability for reference standard of RF power |  | January 2012 | SMU (SK) | Marek Ralbovský | SK, CZ | SMU, CMI | New template was provided | [6 empty] | ongoing | ongoing
completed since TC-EM meeting 2013
Last update: | 2014-10-07 | François Piquemal
Note on A3: Green cells are for project completed and no more to be reported in the Annual report. In case of comparisons, they should still be taken care of, until results are published in App. B
Note on B3: compar. = comparison cons. = consultation trac. = traceability cooper. = cooperation in research
Note on D3: preliminary - planned - protocol complete - measurements in progress - measurements completed - Draft A report in progress - Draft B report in progress - provisional equivalence, published in [Ref] - approved for equivalence, not yet published - approved for equivalence, published in [Ref].
Note on E3: Date of project agreed

## Completed
Completed Projects (Consultation, Cooperation, Traceability)
Project no. | Type | Title | Project Status | Dates | Coord. NMI (and Country) | Coordinator | Participants Countries | Participants NMIs | Action, comment
543 | Consultation | Meeting of experts on the quantum Hall effect and the Josephson effect (now meeting on DC and quantum metrology) | completed | June 01 | UME(TR) | H. Sakarya | TR, BE, CH, CZ, DE, DK, ES, FI, FR, GB, IE, IT, NL, NO, PT, SE, SK, TR | BNM-LNE, CEM, CMI, CTU, DFM, IEN, INETI, JV, METAS, MIKES, NMI-VSL, NML, NPL, PTB, SMD, SMU, SP, UME, UPM (ES), VNIIM, NMIJ, NRC
558 | Consultation | Classification of the calibration and measurement capabilities in the field of electricity and magnetism | completed | Oct 1999 to Nov 2000 | SIQ (SI) | Z. Svetik | SI, CH, GB, IE, IT, NL, SE | IEN, METAS, NPL, NMi-VSL, NML, SIQ, SP
560 | Consultation | Analysis of the calibration and measurement capabilities of the NMIs in the field of electricity and magnetism | completed | Nov 1999 Nov 2000 | NPL (GB) | L. Henderson | GB, AT, BE, CH, CZ, DE, DK, ES, FI, FR, HU, IE, IT, NL, NO, PL, PT, SE, SI, SK, TR | NPL, BEV, SMD, OFMET, CMI, PTB, DFM, CEM, MIKES, BNM-LCIE, OMH, NML, IEN, NMI-VSL, JV, GUM, INETI, SP, SIQ, SMU, UME, BIPM, VMT/VMC, CENAM, CSIR-NML
586 | Consultation | Annual meeting of the Electricity Contact Persons | completed | Jan 2000 to Nov 2000 | CMI (CZ) | J. Streit | CZ, AT, BE, CH, DE, DK, FI, FR, GB, GR, HU, IE, IT, NL, NO, PL, PT, SE, SI, SK, TR | BEV, BNM-LNE, CMI, DFM, EIM, GUM, IEN, INETI, JV, METAS, MIKES, NMi-VSL, NML, NPL, OHM, PTB, SIQ, SMD, SMU, SP, UME, CSIR-NML, VMT/VMC, BIPM
606 | Consultation | Annual meeting of the Electricity Contact Persons | completed | Feb 2001 to Nov 2001 | CMI (CZ) | J. Horska | CZ, AT, BE, CH, DE, DK, ES, FI, FR, GB, GR, HU, IT, NL, NO, PT, SE, SI, SK | BEV, BNM-LNE, CEM, CMI, DANIAMET-AREPA, EIM, IEN, INETI, JV, METAS, MIKES, NMi-VSL, NPL, OHM, PTB, SIQ, SMD, SMU, SP, STU-Gliwice (CZ), AIST (JP), CSIR-NML, CSIRO-NML, NIST, NRC, VNIIM
614 | Consultation | Regular meeting of the AC-DC transfer experts | completed | Feb 2001 to May 2001 | IEN (IT) | G. Marullo Reedtz | IT, FR, NO, CH, FI, NL, GB, DE, SI, BE, SE, TR
620 | Consultation | Analysis of the calibration and measurement capabilities (CMC) of the NMIs in the field of electricity and magnetism - Application of Euromet Guides 8 and 9. | completed | 2001-04-01 | DFM (DK) | K. Carneiro | DK, FR,
642 | Consultation | Evaluation of a national reference laboratory for HF-Electricity and primary laboratory for AC-Electricity | completed | to Oct 2001 | JV (NO) | H. Slinde |  | All labs and guest from outside Euromet
684 | Consultation | Contact Persons Electricity meeting | completed | Summer 2002 | LNE-LAMA (FR) | D. Allal | FR and others
686 | Consultation | Analysis of the results of a measurement comparison | completed | 2002-11-01 | PTB (DE) | H. Bachmair | FR, GR, RO, LV, BU, HR, YU | BNM-LPMO, EIM, INM, LNMC, NCM, PEL, ZMDM
689 | Consultation | Euromet LF experts group meeting, AC-DC transfer difference | completed | 2002-11-01 | GUM (PL) | D. Sochocka | PL | All members, associates and guests of the TCEM
699 | Consultation | Contact Person Electricity meeting | completed | 2003-02-01 | PTB (DE) | Hans Bachmair | AT, DK, DE, FI, FR, IT, NL, SE, CH | BEV, DFM, PTB, MIKES, LPMO, IEN, NMi-VSL, SP, METAS
704 | Consultation | Euromet RF & Microwave Technical Committee Meeting, 2003 | completed | March 2003 | METAS (CH) | Blaise Jeanneret | CH | All members and Associates of EUROMET
709 | Consultation | Euromet DC and Quantum Metrology meeting | completed | 2003-04-01 | SIQ (SI) | Zoran Svetik | SI | All members and Associates of EUROMET
726 | Consultation | Workshop on cw power measurement technical options and on MEMS and micromachining for rf and microwave measurement | completed |  | PTB (DE) | Ralf Behr | CH, DE, FI, FR, NL, SE, UK | METAS, PTB, MIKES, LNE, NMi-VSL, SP, NPL
773 | Consultation | CMC analysis, 3rd round | completed | April 2004 to Dec 2004 | METAS (CH) | Beat Jeckelmann | CH | All Members and Associates of EUROMET
798 | Consultation | Annual Contact Persons meeting of the TCEM | completed |  | EIM (GR) | Irene Flouda | all EUROMET Members and associates | all EUROMET Members and associates
825 | Consultation | CMC analysis, 4th round | completed | Oct 2004 to March 2005 | LNE (FR) METAS (CH) | Francois Piquemal Beat Jeckelmann |  | Other interested instituts
826 | Consultation | LF Experts Meeting | completed | Dec 2004 to Aug 2005 | MIKES | Antti Manninen | all members and associates of EUROMET | all members and associates of EUROMET
829 | Consultation | EUROMET expert meeting on quantum electrical metrology | completed | Jan 2005 to May 2005 | Nmi-VSL | Gert Rietveld | all members and associates of EUROMET | all members and associates of EUROMET
842 | Consultation | EUROMET HF experts group meeting | completed | Dec 2004 to Apr 2'005 | SIQ (SI) | Zoran Svetik | SI
850 | Consultation | EUROMET Contact Persons Meeting | completed | June 2005 to Oct 2005 | METAS (CH) | Beat Jeckelmann | CH
915 | Consultation | 19th meeting of the EUROMET Electricity Contact Persons | completed | Oct 2005 to Oct 2006 | EIM (GR) | Irene Flouda | all EUROMET Members and associates
923 | Consultation | International School"Quantum Metrology and Fundamental Constants | completed | Nov 2006 to Nov 2007 | LNE (FR) METAS (CH) | Francois Piquemal Beat Jeckelmann
933 | Consultation | Meetings of the HF Subfield | completed | Dec 2006 to Apr 2007 | Nmi-VSL | Gert Rietveld | all members and associates of EUROMET
1013 | Consultation | Peer review of the department of electrical quantities | completed | 17.10.2007 to 15.09.08 | METAS (CH) | Beat Jeckelmann | CH, CS, DE | DMDM, PTB, METAS
1043 | Consultation | Peer review of the self declared quality system of the LNE | completed | 01.07.2008 to 0812.2008 | LNE (FR) | Francois Piquemal | FR, CH, IT | LNE, METAS, INRIM | Final report received on 8 Dec 2008
1044 | Consultation | Meeting of high voltage experts | completed | 06.05.2008 to 15.09.2008 | MIKES (FI) | Jari Hällström | CZ, FI, FR, IT, SE, SP, TR, RU, AU, JP | CMI, INRIM, LCOE, LNE, MIKES-TKK, SP, UME, VNIIMS, NMIA, China Institute of Technology
1052 | Consultation | Peer review of the self declared quality system of EIM | completed | 24.06.2008 to 10.10.08 | EIM (GR) | Eirini Flouda | GR, DE | EIM, PTB
1060 | Consultation | Peer review of the Electrical Laboratory of the National Metrology Laboratory, Enterprise Ireland, Dublin | completed | 30.06.2008 to 16.02.09 | NML (IE) | Oliver Power | IE, CH, DE | NML, METAS, PTB | Final report received on 16 Feb 2009
1102 | Consultation | Peer review of VSL's impedance measurement facilities | completed | 06.04.2009 to 21 Oct 2010 | VSL (NL) | Gert Rietveld | DE, NL | PTB, VSL | Final report received 21 Oct. 2010
1122 | Consultation | Workshop of high voltage experts | completed | 02.07.2009; completed Jan 2010 | MIKES (FI) | Jari Hällström | CZ, IT, ES, FR, FI, SE, TR, RU, AU, JP | CMI, INRIM, LCOE, LNE, MIKES, SP, UME | completed 29 Jan 2010
472 | Cooperation | AC properties of the quantum Hall resistance | completed |  | PTB (DE) | J. Melcher | DE, CH, CZ, DE, FR, GB, IE, IT, NL, PT, SE | BNM-LNE, CTU, IEN, INETI, METAS, NMi-VSL, NML, NPL, PTB, SP, CSIRO-NML, NRC, NIST, BIPM
540 | Cooperation | AC QHR sample holder | completed |  | METAS (CH) | B. Jeanneret | CH, ES, GB, NL, NO, SE, TR | METAS, CEM, NPL, NMi-VSL, JV, SP, UME, BIPM
541 | Cooperation | Acquisition of high quality rotary switches | deleted |  | SP (SE) | H. Nilsson | SE, BE, CH, DE, IT, FR
554 | Cooperation | Traceability of Josephson standards | completed |  | PTB (DE) | H. Bachmair | DE, GB, NL | PTB, NPL, NMi-VSL, BIPM
559 | Cooperation | Construction of high resistance measurement standards | completed | Nov 1999 to Oct 2007 | IEN (IT) | G. Marullo Reedtz | IT, CH, CZ, DE, FR, GB, NL, NO, SE, SI | IEN, METAS, CMI, PTB, BNM-LCIE, NPL, NMi-VSL, JV, SP, SIQ
613 | Cooperation | RF impedance standards and traceability for four-terminal pair and related measurements at frequencies from 1 MHz to above 30 MHz | completed | 07.02.2001 to 03.11.09 | NPL (GB) | R. N. Clarke | GB, BE, SI | NPL, SMD, SIQ | final report received 3 Nov 2009
626 | Cooperation | Analysis of different measurement set-ups for a programmable Josephson voltage standard | completed |  | BNM-LNE (FR) | M. Chambon | FR, AT, ES, CZ, DK, GR, PL, IT, PT, NO, CH, FI, NL, IE, GB, HU, DE, SI, BE, SK, SE, TR | BNM-LNE, BEV, CEM, CMI, DFM, EIM, GUM, IEN, INETI, JV, METAS, MIKES, NMI-VSL, NML, NPL, OMH, PTB, SIQ, SMD, SMU, SP, UME, FBMPM, INMETRO, LNMC, NCM, VMT/VMC, BIPM, FBMPM, INMETRO, LNMC, NCM, VMT/VMC, BIPM
631 | Cooperation | Electrical nanometrology | completed |  | IEN (IT) | G. Marullo Reedtz | IT, NL, DE | IEN, NMi-VSL, PTB, BIPM
645 | Cooperation | QHE resistance standard with DVM and JAVS readout |  | completed | BEV (AT) | W. Waldmann | AT + others | NMi-VSL, DFM, NPL, SP, IEN, CEM, PTB
646 | Cooperation | Guidelines for the evaluation of uncertainty budgets for JAVS and QHE based calibrations | completed |  | NPL (GB) | R N Clarke | GB + others | METAS, BNM-LNE, DFM, GUM, IEN, MIKES, NMi-VSL, NPL, PTB, SMU, SP, BIPM
681 | Cooperation | Bilateral comparison on power measurements between UME and PTB | completed |  | SMU (SK) | P. Vrabcek | SK + others | SMU, UME, PTB
700 | Cooperation | Gold plated copper lugs for precision dc voltage measurements | completed | completeded | SP (SE) | Karl Erik Rydler | SE, all interested labs | Members and Associastes of EUROMET and guests
756 | Cooperation | Synthesis of arbitrary waveforms using the Josephson effect | completed | Dec 2003 to April 2010 | NPL (UK) | J Williams | FR, NL, DE, SI, SE, SK, CH, FI, PL, IT | LNE, VSL, PTB, SIQ, SP, SMU, METAS, MIKES, GUM, IEN | Final report received 22 April 2010
817 | Cooperation | Metrological applications of single-electron transport | completed | Oct 2004 to April 2010 | NPL (UK) | Stephen Giblin | UK, DE, SE, FR, NL, CH, FI | NPL, PTB, SP, LNE, NMi, METAS, MIKES | Final report received 22 April 2011
840 | Cooperation | Reference standards for ac-dc voltage and current transfer |  |  | SP (SE) | Karl-Erik Rydler | SE, CH | METAS, SP | METAS, SP
848 | Cooperation | Binary Josephson Array Power Standard | completed | June 2005 to Dec 2007 | PTB (DE) | Ralf Behr | DE
856 | Cooperation | Study and validationof Quantum Hall Array Resistance Standards | completed | July 2005 to Dec 2009 | LNE (FR) | Wilfrid Poirier | CH, DE, FI, FR, UK, CA | METAS, PTB, MIKES, LKNE, NPL, NRC | Final report received 14 Dec 2009
929 | Cooperation | Meetings of the DC and Quantum Metrology and Low Frequency Subfields | completed | Feb 2007 to June 2007 | MIKES | Antti Manninen | all members and associates of EUROMET
1009 | Cooperation | Reference standards for ac-dc current transfer | completed | March 2007 to May 2009 | SP (SE) | Karl-Erik Rydler | AT, SE | BEV, SP | completed 19 May 2009
1010 | Consultation | Revision of the calibration guide for oscilloscopes | completed | October 2007 | PTB (DE) | Hans Bachmair replaced by Rolf Judaschke | all members and associates of EUROMET | all members and associates of EUROMET | Completed project since TCEM meeting 2011 | [8 empty] | Revision of the calibration guide for oscilloscopes: Work is on-going and a meeting is planned for October when this will go to subcommittee. Responsible contact, Rof Judaschke, PTB Project completed
1174 | Cooperation | Study of capacitance loss factor standards at 10 kV level | completed | 2011-01-01 | MIKES (FI) | Jari Hällström | FI, RU | MIKES, VNIIM | Completed project since TCEM meeting 2011
754 | Traceability | Calibrations on high-frequency impedances | completed | Oct 2003 | PTB (DE) | H. Bachmair | DE, UK | PTB, NPL | Project closed since Feb 2013 | [5 empty] | It was decided to write a short progress report every year. | ongoing | ongoing
648 | Cooperation | The Challenge of New Technologies in Electrical Metrology at RF, Microwave and Higher Frequencies. | completed | 2002-03-01 | NPL (GB) | R. N. Clarke | GB, AT, CZ, FI, FR, DE, GR, HU, IT, NL, SE, CH, TR | NPL, BEV, CMI, MIKES, BNM-LNE, PTB, EIM, OMH, IEN, NMi-VSL, SP, METAS, UME | Final report received, March 2013 Project closed | This project was adopted at the HF sub-field meeting in November 2001. It is concerned with cross-European collaboration to ensure that an effective metrological capability can be developed within Europe to support new RF, microwave and millimeter-wave to | No update available | A workshop will be organised during the next RF expert meeting in Spring 2003. Progress form to TC chairman before end of Feb. 2003 | A meeting of BNM-LNE, PTB and NPL was held in September 2002 at NPL, under a project funded by UK NMS. A meeting of all participants will take place at NPL after the HF sub-field meeting planned for March 31, 2003. A separate workshop on the application | A meeting of BNM-LNE, PTB and NPL was held in September 2002 at NPL, under a project funded by UK NMS. A meeting of all participants has taken place at NPL at the beginning of April this year, after the HF sub-field meeting. A separate workshop on the a | Project will be continued. The next meeting is scheduled for the end of 2004 together with a seminar held at BNM/LNE. | The project will be continued with a workshop "The Challenge of New Technologies" which is organized by LNE and will be held at 6 December in Paris | Euromet 648 was set up to investigate opportunities for collaboration in new research areas that could be carried out cost-effectively by cross-NMI research teams. (Such projects would be independent Euromet projects spun of from Euromet 648). A successfu
Note on A3: Green cells are for project completed and no more to be reported in the Annual report. In case of comparisons, they should still be taken care of, until results are published in App. B
Note on B3: compar. = comparison cons. = consultation trac. = traceability cooper. = cooperation in research
Note on D3: preliminary - planned - protocol complete - measurements in progress - measurements completed - Draft A report in progress - Draft B report in progress - provisional equivalence, published in [Ref] - approved for equivalence, not yet published - approved for equivalence, published in [Ref].
Note on E3: Date of project agreed
Note on I4: not sorted
Note on I5: not sorted
Note on I7: not sorted
Note on I8: not sorted
Note on K10: not sorted
Note on K14: not sorted
Note on I36: not sorted
Note on I44: not sorted
Note on J44: not sorted